| Welcome, Inc. 90 – Day Action Plan October 1, 2021 – December 31, 2021 Goal 1 Lead Public Policy Agenda______________________ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Action Steps | Accountability | Timeline | Resources Needed | Success Metrics |
| #1 Chair citywide effort to target one or two policy initiatives | - Reach out to key collaborators & partners | Board Public Policy Chair & board committee | 10/1/21 – 11/15/21 | Compile list Call/email | Committee formed with support from city leaders and key partners; Policy initiative identified |
|  | - Meet with mayor | Board Chair Executive Director | By 11/15/21 | Not applicable |  |
|  | - Draft policy initiative | Board Public Policy Committee | By 12/31/21 | Point person to draft policy |  |
| #2 Engage board members in leading policy agenda |  |  |  |  |  |